# Scrip & Purse – Next Steps Roadmap (UK Spearhead)

## 1. Legal & Regulatory Foundation

- 1.1 Register Society

  - Draft Credit Union Rules (using ABCUL model rules, adapted to faith-based common bond).

  - Submit application to the FCA Mutuals Team under the Co-operative and Community Benefit Societies Act 2014.

- 1.2 Common Bond Wording (Christian-based)

  - “Membership is open to individuals who profess the Christian faith, and to members of Christian fellowships, churches, and organisations in the United Kingdom. Membership is also open to legal persons and organisations whose objects and activities are consistent with, and not contrary to, the Christian faith.”

  - Define “Christian faith” in Rules (Apostles’/Nicene Creed).

- 1.3 Compliance & Registration

  - Register with:

    - PRA & FCA (dual regulation) → prudential + conduct.

    - FSCS (Financial Services Compensation Scheme) → £85k deposit protection.

    - FOS (Financial Ombudsman Service) → complaints handling.

    - ICO (Information Commissioner’s Office) → GDPR compliance.

## 2. Governance & Organisational Setup

- 2.1 Founders & Directors

  - Recruit minimum 21 founder members (individuals + possibly church/legal entities).

  - Identify Board of Directors (min. 5 recommended, including Chair, Treasurer, Compliance Lead).

  - Ensure at least 2 directors meet FCA/PRA “fit and proper” tests (financial services experience preferred).

- 2.2 Membership Charter

  - Define rights: vote, save, borrow, access services.

  - Define duties: uphold Christian ethos, compliance, financial responsibility.

- 2.3 Policies & Controls

  - AML/KYC Policy.

  - Lending Policy (ethical, no usury, mission-aligned).

  - Risk Management Framework.

  - Conflict of Interest Policy.

  - Complaints Handling Procedure.

## 3. Business & Financial Planning

- 3.1 Business Plan (3–5 years)

  - Target membership growth (e.g., 500 members in Year 1, scaling to 5,000+ by Year 5).

  - Product roadmap:

    - Year 1 → savings, ethical loans.

    - Year 2 → debit card, online banking.

    - Year 3 → mortgages, housing co-op finance.

  - Income sources:

    - Loan interest (within FCA credit union limits).

    - Member fees (if any).

    - Grants, donations (possible in early stage).

- 3.2 Financial Projections

  - Capital adequacy (min. £10k–£50k startup).

  - Liquidity ratio planning.

  - Surplus allocation → reserves vs member dividend.

## 4. Technical & Infrastructure

- 4.1 Core Banking System

  - Choose between Credit Union Software providers (e.g., Kesho, CU Apps, FinTech platforms).

  - Ensure compliance with FCA IT security standards.

- 4.2 Payment Rails

  - Partner with Banking-as-a-Service provider (ClearBank, Modulr, Railsr) for early account and card issuance.

  - Transition to direct rails once scale achieved.

- 4.3 Data Security & Compliance

  - Implement GDPR-compliant member database.

  - ISO 27001 alignment for data management.

## 5. Strategic & Community Rollout

- 5.1 Pilot Launch

  - Target churches, Christian fellowships, and Christian professional networks in London, Manchester, Birmingham as first hubs.

  - Run financial literacy workshops linked to Purse launch.

- 5.2 Marketing & Branding

  - Brand as “The Christian Credit Union” (strapline: “Occupy till I come”).

  - Build trust narrative: FSCS-backed, community-driven, Kingdom mission.

- 5.3 Future Alignment with Scrip (Investment Arm)

  - Keep Purse strictly credit-union focused.

  - Begin parallel design of Scrip Capital LLP/Ltd for trading/investment desk (later FCA authorisation).

## 6. Immediate Action Plan (0–90 Days)